## 2017 DETAIL NS STATUS
| PATROL RUN SUMMARIES FOR 2017 | [17 empty] | % of Verified and updated unauth PATONs. | % of Verified, Rechecked and updated unauth PATONs.
|  | 2018-01-01 |  | PATON OBJECTIVES | [9 empty] | COMPARISON TO PLAN
| RUNS BY DIV | Location | TOTAL PATONs | VERIFY PATONS | CHECK PATONS | NEED PHOTO | BRDGE PLAN | UNAUT AIDS | COMPLETED TO DATE |  |  |  |  | PATON RESULTS |  | ON | BRIDGE RESULTS
|  | PRIORITY |  | ONE | TWO | FOUR | THREE | FIVE | VER | CHK | PHO | UNA | BDG |  |  | GOAL
| LIST ONE | SUMMARIES BY AUXILIARY DIVISION
RUNS | DIV 1 | Northern Maine | TOTAL | ONE | TWO | FOUR | THREE | FIVE | VER | CHK | PHO | UNA | BDG | TO GO | % COMP | On Goal | TO GO | % COMP
1 | POC | Off-Shore Aids | 3 | 1 | 0 | Done |  | 0 | 1 | 0 |  | 0 |  | 0 | 33.33% | YES | NONE
2 | 01N | Penobscott River | 10 | 2 | 2 | 2 |  | 6 | 2 | 2 |  | 0 |  | 0 | 40% | YES | NONE
3 | 01C | Penobscott Center | 49 | 7 | 3 | 5 |  | 35 | 5 | 2 |  | 28 |  | 3 | 71.43% | YES | NONE
4 | 01S | Penobscott South | 14 | 1 | 0 | Done |  | 15 | 1 | 0 |  | 15 |  | 0 | 114.3% | YES | NONE
5 | 3 | Eggemoggin Reach | 21 | 4 | 0 | 15 |  | 9 | 4 | 0 | 11 | 2 |  | 0 | 28.57% | NO | NONE
6 | 4 | Jerico Bay | 18 | 4 | 0 | 4 |  | 6 | 4 | 0 | 1 | 0 |  | 0 | 22.22% | NO | NONE
7 | 5 | Blue Hill Bay | 25 | 9 | 2 | 10 |  | 0 | 9 | 2 |  | 0 |  | 0 | 44% | YES | NONE
8 | 6 | Frenchman Bay | 21 | 9 | 5 | 14 |  | 4 | 2 | 2 | 6 | 0 |  | 10 | 19.05% | NO | NONE
9 | 7 | Eastern Bay | 12 | 4 | 2 | 8 |  | 0 | 4 | 0 |  | 0 |  | 2 | 33.33% | YES | NONE
10 | 8 | Jonesport | 28 | 4 | 5 | 24 |  | 0 | 0 | 0 |  | 0 |  | 9 | 0% | NO | NONE
11 | 10 | Eastport | 14 | 4 | 5 | 6 |  | 0 | 0 | 0 |  | 0 |  | 9 | 0% | NO | NONE
12 | BRIDGES | Division 1 Bridges |  | THREE: 8; BDG: 8 | Bridges only |  |  | 0 | 100%
| TOTAL | DIVISION 1 | 215 | 49 | 24 | 88 | 8 | 75 | 32 | 8 | 18 | 45 | 8 | 33 | 39.53% | YES | 0 | 100% | 35.81% | 39.53%
|  | PATONS represent | 8.535% | of the total PATONs in D1NR |  | BRIDGES represent | 4.52% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 22.79% | 2017 Verified, Checked and Added Aid % |  |  | 39.53%
| Runs | Qualified and current AVs in this Division | AVCs | ONE: Total AVs in Division; TWO: Total AV support in 2017; FOUR: Work Level for 2017; THREE: Outside support available?; PHO: COMMENTS
| 12 | 2 | 0 | ONE: 9; TWO: 2; FOUR: HIGH; THREE: None available at this time.; FIVE: There are nine AVs listed in Division 1. Nancy Plunket is the ADSO-NS for ANT SWH. Bex*, Eggleston*, Herman, Lambert A.*, Lambert T.*, Lear*, Ozog*, Sawyer*.
The Aid Verifiers in Division 1 need to be reviewed to identify those AVs who have not been active. The AVs with an asterisk are considered questionable and represent approximately 78% of the available AVs. The ratio of rechecks to scheduled verified is high at 49%. The number of scheduled verifications and rechecks is almost 33%. This statistic indicates that the owners are not reacting to the CG-7054 PATON Reports. The number of delinquent photos also needs attention. The 8 bridges in the Division 1 AOR were surveyed in 2018. 45 "Unauthorized" private aids listed in Division 1 were resolved and added to the Harbormaster System in 2017.
RUNS | DIV 2 | Southern Maine | TOTAL | VER | CHK | PHOTO | BDG | UNAUT | VER | CHK | PHO | UNA | BDG | TO GO | % COMP | On Goal | TO GO | % COMP
1 | D 2 - POC-SP | ADSO-NS | 1 | ONE: 0; TWO: 1; FOUR: 1; VER: 0; CHK: 0 | 1 | 0% | NO | NONE
2 | D 2 - BH1 | BOOTHBAY HBR RUN | 64 | 31 | 4 | 29 |  |  | 23 | 1 | 1 |  |  | 11 | 37.5% | YES | NONE
3 | D 2 - BH2 | UPPER KENEBEC R. RUN | 20 | ONE: 0; TWO: 7; FOUR: 10; VER: 0; CHK: 0 | 7 | 0% | NO | NONE
4 | D 2 - BH3 | SHEEPSCOTT R. RUN | 27 | 18 | 2 | 13 |  | 1 | 14 | 0 |  |  |  | 6 | 51.85% | YES | NONE
5 | D 2 - BH4 | MUSCONGUS BAY RUN | 11 | ONE: 11; TWO: 0; FOUR: 11; VER: 11; CHK: 0 | 0 | 100% | YES | NONE
6 | D 2 - BH5 | BH Bridge Run |  | THREE: 14; BDG: 14 | Bridges only |  |  | 0 | 100%
7 | D 2 - CB1 | CASCO BAY AREA 1 RUN | 50 | 21 | 23 | 12 |  | 2 | 21 | 19 |  |  |  | 4 | 80% | YES | NONE
8 | D 2 - CB2 | CASCO BAY AREA 2 RUN | 4 | ONE: 0; TWO: 0; FOUR: Done; VER: 0; CHK: 0 | 0 | 0% | NS | NONE
9 | D 2 - CB3 | CASCO BAY AREA 3 RUN | 20 | 11 | 4 | 13 |  |  | 11 | 4 | 4 |  |  | 0 | 75% | YES | NONE
10 | D 2 - CB4 | Casco Bay Bridge Run |  | THREE: 10; BDG: 8 | Bridges only |  |  | 2 | 80%
11 | D 2 - PH1 | Portsmouth Harbor RUN | 29 | ONE: 13; TWO: 4; FOUR: 8; VER: 11; CHK: 4 | 2 | 51.72% | YES | NONE
12 | D 2 - PH2 | Hampton Harbor RUN | 6 | ONE: 6; TWO: 0; FOUR: 2; VER: 0; CHK: 0 | 6 | 0% | NO | NONE
13 | D 2 - PH3 | PH Bridges Run |  | THREE: 20; BDG: 1 | Bridges only |  |  | 19 | 5%
14 | D 2 - SB | SACO BAY RUN | 17 | 17 | 0 | 1 |  |  | 17 | 0 | 1 |  |  | 0 | 100% | YES
| TOTAL | DIVISION 2 | 249 | 128 | 45 | 100 | 44 | 3 | 108 | 28 | 6 | 0 | 23 | 37 | 54.62% | YES | 21 | 52.27% | 43.37% | 54.62%
|  | PATONS represent | 9.885% | of the total PATONs in D1NR |  | BRIDGES represent | 24.86% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 51.41% | 2017 Verified, Checked and Added Aid % |  |  | 54.62%
| Runs | Qualified and current AVs in this Division | AVCs | ONE: Total AVs in Division; TWO: Total AV support in 2017; FOUR: Work Level for 2017; THREE: Outside support available?; PHO: COMMENTS | [8 empty] | 5
| 14 | 14 | 0 | ONE: 23; TWO: 14; FOUR: HIGH; THREE: None available at this time.; FIVE: There are twenty-three AVs in Division 2. Bill Thornton is the ADSO-NS for ANT South Portland. Abbott*, Boselli, Byrne, Chatham*, Ciolino, Clancy*, Dehne*, Dempsey*, Eastwood, Esser*, Grieg*, Homer, Johnson*, Katz, Maccormac, Nash*, Power, JR., Raynor, Rubichaud, Schwinn, Stobo, and Thompson*.
The Aid Verifiers in Division 2 need to be reviewed to identify those AVs who have not been active. The AVs with an asterisk are considered questionable and represent approximately 39% of the available AVs. The ratio of rechecks to scheduled verified is high at 35%. The number of scheduled verifications and rechecks is almost 69.5%. This statistic indicates that the owners are not reacting to the CG-7054 PATON Reports. The number of delinquent photos also need attention in 2018. Only 52.3 % bridges in the Division 1 AOR were surveyed in 2018.
RUNS | DIV 3 | MA North Rivers | TOTAL | VER | CHK | PHOTO | BDG | UNAUT | VER | CHK | PHO | UNA | BDG | TO GO | % COMP | On Goal | TO GO | % COMP
1 | D 3 - NBP-1 A | Salisbury Run Sheets | 4 | ONE: 0; TWO: 1; FOUR: 1; VER: 0; CHK: 0 | 1 | 0% | NO | NONE
2 | D 3 - NBP-1 B | Newburyport Run Sheets | 20 | 2 | 9 | 12 | 7 | 2 | 0 | 0 |  |  | 7 | 11 | 0% | NO | 0 | 100% |  |  |  |  | 25
3 | D 3 - NBP-1 C | Haverhill Run Sheets | 6 | 6 | 0 | Done | 1 |  | 0 | 0 |  |  | 1 | 6 | 0% | NO | 0 | 100%
5 | D 3 - NBP-2 | Essex River Run Sheets | 24 | 23 | 0 | 13 | 1 | 1 | 0 | 0 |  |  | 1 | 23 | 0% | NO | 0 | 100%
6 | D 3 - NBP-3 | Parker River Run Sheets | 19 | 19 | 0 | 10 | 1 | 10 | 19 | 0 |  | 10 | 1 | 0 | 152.6% | YES | 0 | 100% |  |  | HMRAP
7 | D 3 - NBP 4 | Ipswich River Run Sheets | 33 | ONE: 30; TWO: 2; FOUR: 32; VER: 30; CHK: 2 | 0 | 96.97% | YES | NONE |  |  |  | HMRAP
8 | D 3 - NS-5 | Annisquam River Run Sheets | 33 | 27 | 0 | 31 | 3 | 5 | 0 | 0 |  |  | 3 | 27 | 0% | NO | 0 | 100%
| TOTAL | DIVISION 3 | 139 | 107 | 12 | 99 | 13 | 18 | 49 | 2 | 0 | 10 | 13 | 68 | 43.88% | YES | 0 | 100%
|  | PATONS represent | 5.518% | of the total PATONs in D1NR |  | BRIDGES represent | 7.345% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 76.98% | 2017 Verified, Checked and Added Aid % |  |  | 43.88%
| Runs | Qualified and current AVs in this Division | AVCs | ONE: Total AVs in Division; TWO: Total AV support in 2017; FOUR: Work Level for 2017; THREE: Outside support available?; PHO: COMMENTS | [8 empty] | 5
| 8 | 0 | 2 | ONE: 2; TWO: 0; FOUR: HIGH; THREE: None available at this time.; FIVE: There are only 2 AVs in Division 3 and both are inactive. There are two AVCs in Division 3 who will be attending AV training starting in February - Mitchell and Strouse.
The Aid Verifiers in Division 3 need to be reviewed to identify those AVs who have not been active. The AVs with an asterisk are considered questionable and represent approximately 39% of the available AVs. The ratio of rechecks to scheduled verified is high at 35%. The number of scheduled verifications and rechecks is almost 69.5%. This statistic indicates that the owners are not reacting to the CG-7054 PATON Reports. The number of delinquent photos also need attention in 2018. All of the bridges in the Division 3 AOR were surveyed in 2017 by Thom Simmons, an AV from Burlington, VT. Use of the HMRAP Program will be used in Newburyport, Essex, Newbury, Ipswivh and Gloucester in 2018 to cover the 2018 PATON and Bridge Plan. Activity in 2017 was handled by AVs from outside of Division 5.
RUNS | DIV 4 | MA North Shore | TOTAL | VER | CHK | PHOTO | BDG | UNAUT | VER | CHK | PHO | UNA | BDG | TO GO | % COMP | On Goal | TO GO | % COMP
1 | D 4 - NS-1 | Saugus River Run | 8 | 5 | 0 | 7 | 4 |  | 0 | 0 | 0 | 0 | 3 | 5 | 0% | NO | 1 | 75%
2 | D 4 - NS-2 | Marblehead, Harbor Run | 22 | 13 | 1 | 11 |  |  | 0 | 0 | 0 | 0 |  | 14 | 0% | NO | NONE
3 | D 4 - NS-3A | Salem Harbor Run | 6 | 5 | 0 | 5 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 5 | 0% | NO | 0 | 100%
4 | D 4 - NS-3B | Palmer Cove YC Run | 17 | 13 | 0 | 2 |  |  | 13 | 0 | 0 | 0 |  | 0 | 76.47% | YES | NONE |  |  |  | HMRAP
5 | D 4 - NS-3C | Dion Yacht Yard Run | 11 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 0 |  | 11 | 0% | NO | NONE
6 | D 4 - NS-4A | Beverly Harbor Run | 11 | 7 | 0 | 6 | 2 | 4 | 0 | 0 | 0 | 0 | 2 | 7 | 0% | NO | 0 | 100%
7 | D 4 - NS-4B | Danvers River Run | 16 | 16 | 0 | 2 | 1 |  | 0 | 0 | 0 | 0 | 1 | 16 | 0% | NO | 0 | 100%
| TOTAL | DIVISION 4 | 91 | 70 | 1 | 44 | 8 | 5 | 13 | 0 | 0 | 0 | 7 | 58 | 14.29% | NO | 1 | 87.5% | 14.29% | 14.29%
|  | PATONS represent | 3.613% | of the total PATONs in D1NR |  | BRIDGES represent | 4.52% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 76.92% | 2017 Verified, Checked and Added Aid % |  |  | 14.29%
| Runs | Qualified and current AVs in this Division | AVCs | ONE: Total AVs in Division; TWO: Total AV support in 2017; FOUR: Work Level for 2017; THREE: Outside support available?; PHO: COMMENTS | [8 empty] | 5
| 7 | 0 | 3 | ONE: 3; TWO: 0; FOUR: HIGH; THREE: None available at this time.; FIVE: There are only 3 AVs in Division 3. Only 1 is active - - - Cusack, Amiro* and Pierce*. There are two AVCs in Division 3 who will be attending AV training starting in February - - - Wilson and Wills. Divison 5 support was unable to reach Division 4 this year due to weather and crew scheduling difficulties.
The Aid Verifiers in Division 3 need to be reviewed to identify those AVs who have not been active. The AVs with an asterisk are considered questionable and represent approximately 100% of the available AVs. The ratio of rechecks to scheduled verified is very low which is great. The number of scheduled verifications and rechecks is almost 14.3%. The number of delinquent photos also need attention in 2018. All of the bridges in the Division 3 AOR were surveyed in 2017 by Thom Simmons, an AV from Burlington, VT. A NS Team is currently forming in 2018 which should be able to handle the plan. Options are available for HMRAP Runs in Marblehead, Beverly and Danvers in 2018.
RUNS | DIV 5 | INNER BOS HARBOR | TOTAL | VER | CHK | PHOTO | BDG | UNAUT | VER | CHK | PHO | UNA | BDG | TO GO | % COMP | On Goal | TO GO | % COMP
1 | D 5 - BOS-AA | ANT BOSTON Run | 28 | 28 | 0 | Done |  |  | 28 | 0 | 0 | 0 |  | 0 | 100% | YES | NONE
2 | D 5 - BOS-1A | Boston Inner Harbor Run | 21 | 14 | 5 | Done |  |  | 14 | 5 | 0 | 0 |  | 0 | 90.48% | YES | NONE
3 | D 5 - BOS-1B | Winthrop Run | 23 | 9 | 14 | 2 |  |  | 9 | 14 | 0 | 0 |  | 0 | 100% | YES | NONE
4 | D 5 - BOS-02 | Dorchester Bay Run | 38 | 15 | 23 | 1 | 3 | 3 | 15 | 23 | 0 | 3 | 3 | 0 | 107.9% | YES | 0 | 100%
5 | D 5 - BOS-1C | Charles River, BRIDGES |  | THREE: 19; BDG: 19 | Bridges only |  |  | 0 | 100%
6 | D 5 - BOS-1C | Boston Harbor Bridges |  | THREE: 13; BDG: 13 | Bridges only |  |  | 0 | 100%
7 | D 5 - BOS-1E | Mystic River Bridges |  | THREE: 11; BDG: 11 | Bridges only |  |  | 0 | 100%
| TOTAL | DIVISION 5 | 110 | 66 | 42 | 3 | 46 | 3 | 66 | 42 | 0 | 3 | 46 | 0 | 100.9% | YES | 0 | 100% | 62.73% | 100.9%
|  | PATONS represent | 4.367% | of the total PATONs in D1NR |  | BRIDGES represent | 25.99% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 60% | 2017 Verified, Checked and Added Aid % |  |  | 100.9%
| Runs | Qualified and current AVs in this Division | AVCs | ONE: Total AVs in Division; TWO: Total AV support in 2017; FOUR: Work Level for 2017; THREE: Outside support available?; PHO: COMMENTS | [8 empty] | 5
| 7 | 8 | 0 | ONE: 9; TWO: 8; FOUR: HIGH; THREE: None needed at this time.; FIVE: There are nine AVs in Division 5. Only 1 is active - - - Cohen, Eastman*, Isherwood, Kaye, Mansour, Murray, Rothstein, Silvestri, and McKenzie.
The AV with an asterisk is considered questionable and represent approximately 11% of the available AVs. The ratio of rechecks to scheduled verified is high. In 2017, the AVs completed 100% of the PATON and Bridges in Division 5 due to the Sail Boston event in this AOR. A Division 5 NS Team also supported some Runs in Division 12.
RUNS | DIV 6 | Buzzards Bay | TOTAL | VER | CHK | PHOTO | BDG | UNAUT | VER | CHK | PHO | UNA | BDG | TO GO | % COMP | On Goal | TO GO | % COMP
1 | D 6 - DELTA-A | Onset Harbor Run | 30 | 28 | 1 | 23 | 1 |  | 28 | 1 | 17 | 0 | 1 | 0 | 96.67% | YES | 0 | 100%
2 | D 6 - DELTA-B | Wareham Harbor Run | 40 | 21 | 0 | 21 | 1 |  | 21 | 0 | 21 | 0 | 1 | 0 | 52.5% | YES | 0 | 100%
3 | D 6 - ECHO | Marion Harbor Run | 48 | 21 | 9 | 19 |  | 4 | 17 | 4 | 4 | 0 | 0 | 9 | 43.75% | YES | NONE
4 | D 6 - FOX A | Fairhaven, Mattapoisette | 35 | 14 | 6 | 12 | 1 |  | 0 | 4 | 0 | 0 | 1 | 16 | 11.43% | NO | 0 | 100%
5 | D 6 - FOX B | New Bedford, - Cuttyhunk | 28 | 5 | 12 | 6 | 3 |  | 0 | 0 | 0 | 0 | 3 | 17 | 0% | NO | 0 | 100%
14 | D 7 - FOXTROT | Westport River Run | 64 | 43 | 13 | 18 | 0 | 0 | 43 | 13 | 8 | 0 |  | 0 | 87.5% | YES | NONE
| TOTAL | DIVISION 6 | 245 | 132 | 41 | 99 | 6 | 4 | 109 | 22 | 50 | 0 | 6 | 42 | 53.47% | YES | 0 | 100% | 44.49% | 53.47%
|  | PATONS represent | 9.726% | of the total PATONs in D1NR |  | BRIDGES represent | 3.39% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 53.88% | 2017 Verified, Checked and Added Aid % |  |  | 53.47%
| Runs | Qualified and current AVs in this Division | AVCs | ONE: Total AVs in Division; TWO: Total AV support in 2017; FOUR: Work Level for 2017; THREE: Outside support available?; PHO: COMMENTS | [8 empty] | 5
| 14 | 8 | 0 | ONE: 9; TWO: 8; FOUR: HIGH; THREE: None needed at this time.; FIVE: There are nine AVs in Division 5. Only 1 is active - - - Cohen, Eastman*, Isherwood, Kaye, Mansour, Murray, Rothstein, Silvestri, and McKenzie.
The AV with an asterisk is considered questionable and represent approximately 11% of the available AVs. The ratio of rechecks to scheduled verified is high. In 2017, the AVs completed 100% of the PATON and Bridges in Division 5 due to the Sail Boston event in this AOR. A Division 5 NS Team also supported some Runs in Division 12.
More positive News - John Stevens, a new AV, has joined the DIV 6 Navigation Systems Team.
SPECIAL NOTE: The Westport River aids and managed by CG ANT Bristol but are located in Division 6's AOR.
RUNS | DIV 7 | Narragansett Bay | TOTAL | VER | CHK | PHOTO | BDG | UNAUT | VER | CHK | PHO | UNA | BDG | TO GO | % COMP | On Goal | TO GO | % COMP
1 | D 7 - ANT BRIS | Block Island Wind Farm RUN | 8 | 8 | 0 | 6 |  |  | 8 | 0 | 0 | 0 |  | 0 | 100% | YES | NONE
2 | D 7 - BI-O | Block Island RUN | 48 | 35 | 0 | 32 |  |  | 35 | 0 | 0 | 0 |  | 0 | 72.92% | YES | NONE
3 | D 7 - C1 | Upper Narragansett Bay RUN | 38 | 19 | 2 | 5 |  | 2 | 19 | 2 | 3 | 0 |  | 0 | 55.26% | YES | NONE
4 | D 7 - C2 | Bristol RUN | 37 | 15 | 4 | 11 |  | 8 | 15 | 2 | 7 | 6 |  | 2 | 62.16% | YES | NONE
5 | D 7 - C3 | Newport RUN | 35 | 9 | 2 | 4 |  | 1 | 8 | 1 | 0 | 0 |  | 2 | 25.71% | NO | NONE
6 | D 7 - C4 | Barrington River RUN | 14 | 13 | 0 | 1 |  |  | 13 | 0 | 1 | 0 |  | 0 | 92.86% | YES | NONE
7 | D 7 - C5 | Coasters Harbor RUN | 6 | 3 | 1 | 3 |  | 1 | 3 | 1 | 1 | 0 |  | 0 | 66.67% | YES | NONE
8 | D 7 - C6 | Newport HM RUN | 26 | 11 | 2 | 1 |  |  | 11 | 2 | 1 | 0 |  | 0 | 50% | YES | NONE
9 | D 7 - E1 | MT Hope Bay RUN | 45 | 20 | 5 | 4 |  | 3 | 20 | 0 | 0 | 0 |  | 5 | 44.44% | YES | NONE
10 | D 7 - E2 | Seconnet River RUN | 31 | 3 | 3 | 4 |  |  | 2 | 0 | 0 | 0 |  | 4 | 6.452% | NO | NONE
11 | D 7 - W1 | Greenwich Bay RUN | 19 | 12 | 5 | 4 |  |  | 10 | 1 | 2 | 0 |  | 6 | 57.89% | YES | NONE
12 | D 7 - W2 | Wickford RUN | 17 | 1 | 3 | 2 |  |  | 1 | 1 | 0 | 0 |  | 2 | 11.76% | NO | NONE
13 | D 7 - W3 | Central Narragansett RUN | 19 | 0 | 12 | 5 |  | 2 | 0 | 12 | 0 | 0 |  | 0 | 63.16% | YES | NONE
15 | D 7 - PJ-O | Point Judith RUN | 43 | 5 | 11 | 20 |  | 3 | 2 | 6 | 0 | 0 |  | 8 | 18.6% | NO | NONE
16 | D 7 - BRDG | Division 7 Bridges |  | THREE: 15; BDG: 15 | Bridges only |  |  | 0 | 100%
| TOTAL | DIVISION 7 | 386 | 154 | 50 | 102 | 15 | 20 | 147 | 28 | 15 | 6 | 15 | 7 | 46.89% | YES | 0 | 100% | 39.64% | 45.34%
|  | PATONS represent | 15.32% | of the total PATONs in D1NR |  | BRIDGES represent | 8.475% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 39.9% | 2017 Verified, Checked and Added Aid % |  |  | 46.89%
|  | Represents | 15.32% | ONE: of D1NR; FOUR: Represents; THREE: 8.475%; FIVE: of D1NR
| Runs | Qualified + Current AVs | Tot AVs | ONE: % of D1NR PATONS; TWO: % of D1NR BRIDGES; VER: COMMENTS
| 15 | 16 | 18 | ONE: 15.32%; TWO: 8.475%; FOUR: The Division 7 NS Teams completed their PATON and Bridge objectives for 2017.
GOOD NEWS - A Great job was done by the Division 7 NS Teams. Division 7 handles 15.5% of the PATONs in First Northern.
NOT SO GOOD NEWS - There is only Good News from Division 7.
RUNS | DIV 9 | Western MA | TOTAL | VER | CHK | PHOTO | BDG | UNAUT | VER | CHK | PHO | UNA | BDG | TO GO | % COMP | On Goal | TO GO | % COMP
1 | Bridges | Conn Riv Bridges |  | THREE: 14; BDG: 11 | Bridges only |  |  | 3 | 78.57%
| TOTAL | DIVISION 9 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 11 | Bridges only |  |  | 3 | 78.57% | 0% | 0%
|  | PATONS represent | 0% | of the total PATONs in D1NR |  | BRIDGES represent | 7.91% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 0% | 2017 Verified, Checked and Added Aid % |  |  | 0%
|  | Represents | 0% | ONE: of D1NR; FOUR: Represents; THREE: 7.91%; FIVE: of D1NR
RUNS | DIV 11 | Cape Cod | TOTAL | VER | CHK | PHOTO | BDG | UNAUT | VER | CHK | PHO | UNA | BDG | TO GO | % COMP | On Goal | TO GO | % COMP
1 | D11 - ANT WH | ANT Woods Hole | 6 | 6 | 0 | Done |  |  | 0 | 0 | 0 | 0 |  | 6 | 0% | NO | NONE
2 | D11 - CAPE-AA | Off Shore Aids | 14 | 2 | 0 | 10 |  |  | 1 | 0 | 0 | 0 |  | 1 | 7.143% | NO | NONE
3 | D11 - MV-A | MV East Area A | 37 | 20 | 1 | 9 |  |  | 10 | 0 | 0 | 0 |  | 11 | 27.03% | NO | NONE
4 | D11 - MV-B | MV North Area B | 18 | 4 | 4 | 3 |  | 1 | 0 | 0 | 0 | 0 |  | 8 | 0% | NO | NONE
5 | D11 - NAN-1 | Nantucket Island 1 | 41 | 22 | 5 | 5 |  |  | 11 | 0 | 2 | 0 |  | 16 | 26.83% | NO | NONE
6 | D11 - NAN-2 | Nantucket Island 2 | 32 | 5 | 0 | Done |  |  | 5 | 0 | 2 | 0 |  | 0 | 15.62% | NO | NONE
7 | D11 - AE-2 | Stage Harbor HMRAP | 39 | 39 | 0 | 15 | 1 |  | 39 | 0 | 0 | 0 | 0 | 0 | 100% | YES | 1
8 | D11 - AE-3 | Southway HMRAP | 28 | 18 | 0 | 11 |  | 4 | 11 | 0 | 0 | 4 |  | 7 | 53.57% | YES | NONE
9 | D11 - AN-2 | Pleasant Bay HMRAP | 76 | 59 | 10 | 65 |  |  | 47 | 10 | 6 | 0 |  | 12 | 75% | YES | NONE
10 | D11 - AN-1 | Wellfleet | 24 | 19 | 3 | 5 |  |  | 19 | 0 | 0 | 0 |  | 3 | 79.17% | YES | NONE
11 | D11 - AN-3 | Little Pleasant Bay | 31 | 4 | 25 | 22 |  |  | 4 | 25 | 0 | 0 |  | 0 | 93.55% | YES | NONE
12 | D11 - AN-4 | Town Cove-Rock Harbor | 28 | 5 | 7 | 19 |  |  | 0 | 0 | 0 | 0 |  | 12 | 0% | NO | NONE
13 | D11 - CW-2 | Sesuit Harbor | 9 | 0 | 2 | 5 |  |  | 0 | 0 | 0 | 0 |  | 2 | 0% | NO | NONE
14 | D11 - AE-1 | ALLEN /HERRING | 17 | 9 | 1 | 8 |  |  | 9 | 1 | 0 | 0 |  | 0 | 58.82% | YES | NONE
15 | D11 - AW-1 | Parkers R.-Hyannis | 26 | 20 | 0 | 12 |  |  | 20 | 0 | 0 | 0 |  | 0 | 76.92% | YES | NONE
16 | D11 - AW-2 | Lower Bass - Weir Riv | 39 | 17 | 5 | 7 |  | 1 | 17 | 5 | 0 | 0 |  | 0 | 56.41% | YES | NONE
17 | D11 - AW-3 | Upper Bass River | 56 | 40 | 2 | 39 | 4 |  | 40 | 2 | 0 | 0 | 4 | 0 | 75% | YES | 0 | 100%
18 | D11 - BE-1 | Poppon/Santuit R. | 42 | 5 | 3 | 6 |  |  | 0 | 0 | 0 | 0 |  | 8 | 0% | NO | NONE
19 | D11 - CS-B2 | Waquoit Bay | 17 | 8 | 0 | 1 | 1 |  | 5 | 0 | 0 | 0 | 1 | 3 | 29.41% | NO | 0
20 | B11 - BE-2 | Cotuit -Seapuit HMRAP | 51 | 7 | 0 | 51 |  |  | 0 | 0 | 0 | 0 |  | 7 | 0% | NO | NONE
21 | D11 - BE-3 | W.- No.-Marston HMRAP | 54 | 0 | 0 | 41 | 1 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0% | N/S | 0
22 | D11 - BE-4 | Cntrvlle-Hyannis HMRAP | 41 | 0 | 3 | 41 |  | 2 | 0 | 0 | 0 | 2 |  | 3 | 4.878% | N/S | NONE
23 | D11 - CW-1 | Barn. Harbor | 19 | 0 | 0 | 12 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0% | N/S | NONE
24 | D11 - CS-A | Falmouth Coast | 27 | 11 | 3 | 3 | 3 |  | 9 | 2 | 0 | 0 | 3 | 3 | 40.74% | YES | 0
25 | D11 - CS-B1 | Waquoit | 35 | 31 | 3 | 3 |  |  | 26 | 1 | 0 | 0 |  | 7 | 77.14% | YES | NONE
26 | D11 - CS-C | West Falmouth | 51 | 23 | 8 | 16 | 1 |  | 16 | 0 | 1 | 0 | 1 | 15 | 31.37% | NO | 0 | 100%
27 | D11 - CS-D | Bourne HMRAP | 40 | 18 | 3 | 6 |  |  | 4 | 0 | 0 | 0 |  | 17 | 10% | NO | NONE
28 | D11 - CS-E | Buttermilk Bay HMRAP | 18 | 15 | 0 | 6 | 5 |  | 2 | 0 | 1 | 0 | 5 | 13 | 11.11% | NO | 0 | 100%
RUNS | TOTAL | DIVISION 11 | 916 | 407 | 88 | 421 | 16 | 8 | 295 | 46 | 12 | 6 | 15 | 154 | 37.88% | YES | 1 | 93.75% | 32.86% | 37.88%
|  | PATONS represent | 36.36% | of the total PATONs in D1NR |  | BRIDGES represent | 9.04% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 44.43% | 2017 Verified, Checked and Added Aid % |  |  | 37.88%
|  | Represents | 36.36% | ONE: of D1NR; FOUR: Represents; THREE: 9.04%; FIVE: of D1NR
| Runs | Qualified + Current AVs | Tot AVs | ONE: % of D1NR PATONS; TWO: % of D1NR BRIDGES; VER: COMMENTS
| 27 | 25 | 27 | ONE: 36.36%; TWO: 9.04%; FOUR: The Division 11 NS Teams completed their PATON and Bridge objectives for 2017.
GOOD NEWS - A Great job was done by the Division 11 NS Teams. Division 11 handles 36.8% of the PATONs in First Northern.
NOT SO GOOD NEWS - There are 11 bridges remaining to be surveyed. The 2017 Bridge report deadline is 12/31.
RUNS | DIV 12 | MA South Shore | TOTAL | VER | CHK | PHOTO | BDG | UNAUT | VER | CHK | PHO | UNA | BDG | TO GO | % COMP | On Goal | TO GO | % COMP
1 | D12 - BOS-3 | Weymouth – Braintree Run | 18 | 7 | 3 | 4 | 3 | 1 | 7 | 3 | 4 | 1 | 3 | 0 | 61.11% | YES | 0 | 100%
2 | D12 - BOS-4 | Hull-Hingham-Weir River Run | 29 | 7 | 11 | 1 |  | 2 | 7 | 11 | 1 | 0 |  | 0 | 62.07% | YES | NONE
3 | D12 - BOS-5 | Scituate Harbor Run | 6 | 0 | 0 | 4 |  | 1 | 0 | 0 | 0 | 0 |  | 0 | 0% | N/S | NONE
4 | D12 - BOS-6B | South River Run | 16 | 1 | 10 | 3 | 2 | 0 | 1 | 10 | 3 | 4 | 2 | 0 | 93.75% | YES | 0 | 100%
5 | D12 - BOS-6C | North River Run | 17 | 5 | 9 | 1 | 2 | 4 | 5 | 9 | 0 | 0 | 1 | 0 | 82.35% | YES | 1 | 50%
6 | D12 - BOS-6D | Herring River Run | 10 | 0 | 0 | 6 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0% | N/S | NONE
7 | D12 - BOS-7A | Duxbury Harbor Run | 28 | 7 | 0 | 0 |  | 1 | 7 | 0 | 0 | 1 |  | 0 | 28.57% | NO | NONE
8 | D12 - BOS-7B | Kingston Harbor Run | 23 | 23 | 0 | 5 |  |  | 23 | 0 | 0 | 0 |  | 0 | 100% | YES | NONE
9 | D12 - BOS-7C | Plymouth Run | 21 | 14 | 7 | 20 |  |  | 14 | 7 | 7 | 0 |  | 0 | 100% | YES | NONE
| TOTAL | DIVISION 12 | 168 | 64 | 40 | 44 | 7 | 9 | 64 | 40 | 15 | 6 | 6 | 0 | 65.48% | YES | 1 | 85.71% | 41.67% | 65.48%
|  | PATONS represent | 6.669% | of the total PATONs in D1NR |  | BRIDGES represent | 3.955% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 38.1% | 2017 Verified, Checked and Added Aid % |  |  | 65.48%
|  | Represents | 6.669% | ONE: of D1NR; FOUR: Represents; THREE: 3.955%; FIVE: of D1NR
| Runs | Qualified + Current AVs | Tot AVs | ONE: % of D1NR PATONS; TWO: % of D1NR BRIDGES; VER: COMMENTS
| 8 | 3 | 4 | ONE: 6.669%; TWO: 3.955%; FOUR: The Division 5 and 12 NS Teams completed the PATON and Bridge objectives for Division 12 in 2017.
GOOD NEWS - A Great support job was done by the Division 5 and 6 NS Teams.
NOT SO GOOD NEWS - Definite need for retraining and a firm commitment from the Division 12 AVs in 2018.
| TOTALS | FIRST NORTHERN | 2519 | 1177 | 343 | 1000 | 177 | 145 | 883 | 216 | 116 | 76 | 150 | 421 | 46.65% | YES | 27 | 84.75% | 38.07% | 46.65%
|  | PATONS represent | 100% | of the total PATONs in D1NR |  | BRIDGES represent | 100% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 46.72% | 2017 Verified, Checked and Added Aid % |  |  | 46.65%
|  |  | 100% | ONE: 100%; THREE: 100% | PATON RESULTS |  | ON | BRIDGE RESULTS
| LIST TWO | SUMMARIES BY COAST GUARD ANT | [13 empty] | GOAL
| LIST THREE | SUMMARY BY CG SECTOR |  | VER: COMPLETED TO DATE | COMPARISON TO PLAN
RUNS | PATROL RUNS FOR USCG ANT | AUXILIARY DIVISIONS | Total PATONs | VER | CHK | PHOTO | BDG | UNAUT | VER | CHK | PHO | UNA | BDG | TO GO | % COMP | Made Goal | TO GO | % COMP
12 | SWH | DIVISION 1 | 215 | 49 | 24 | 88 | 8 | 75 | 32 | 8 | 18 | 45 | 8 | 33 | 39.53% | YES | 0 | 100% | 35.81% | 39.53%
|  | PATONS represent | 8.535% | of the total PATONs in D1NR |  | BRIDGES represent | 4.52% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 22.79% | 2017 Verified, Checked and Added Aid % |  |  | 39.53%
|  | Represents | 8.535% | ONE: of D1NR; FOUR: Represents; THREE: 4.52%; FIVE: of D1NR
14 | SOPORT | DIVISION 2 | 249 | 128 | 45 | 100 | 44 | 3 | 108 | 28 | 6 | 0 | 23 | 37 | 54.62% | YES | 21 | 52.27% | 43.37% | 54.62%
|  | PATONS represent | 9.885% | of the total PATONs in D1NR |  | BRIDGES represent | 24.86% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 51.41% | 2017 Verified, Checked and Added Aid % |  |  | 54.62%
|  | Represents | 9.885% | ONE: of D1NR; FOUR: Represents; THREE: 24.86%; FIVE: of D1NR
32 | BOS | DIVISIONS 3, 4, 5, 9 AND 12 | 508 | 307 | 95 | 190 | 88 | 35 | 192 | 84 | 15 | 19 | 83 | 126 | 58.07% | YES | 5 | 94.32% | 41.54% | 58.07%
|  | PATONS represent | 20.17% | of the total PATONs in D1NR |  | BRIDGES represent | 49.72% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 60.43% | 2017 Verified, Checked and Added Aid % |  |  | 58.07%
|  | Represents | 20.17% | ONE: of D1NR; FOUR: Represents; THREE: 49.72%; FIVE: of D1NR
33 | WH | DIVISIONS 6 AND 11 | 1097 | 496 | 116 | 502 | 22 | 12 | 361 | 55 | 54 | 6 | 21 | 196 | 38.47% | YES | 1 | 95.45% | 33.45% | 38.47%
|  | PATONS represent | 43.55% | of the total PATONs in D1NR |  | BRIDGES represent | 12.43% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 45.21% | 2017 Verified, Checked and Added Aid % |  |  | 38.47%
|  | Represents | 43.55% | ONE: of D1NR; FOUR: Represents; THREE: 12.43%; FIVE: of D1NR
16 | BRIS | DIVISIONS 7 and 10 | 450 | 197 | 63 | 120 | 15 | 20 | 190 | 41 | 23 | 6 | 15 | 29 | 52.67% | YES | 0 | 100% | 43.56% | 52.67%
|  | PATONS represent | 17.86% | of the total PATONs in D1NR |  | BRIDGES represent | 8.475% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 43.78% | 2017 Verified, Checked and Added Aid % |  |  | 52.67%
|  | Represents | 17.86% | ONE: of D1NR; FOUR: Represents; THREE: 8.475%; FIVE: of D1NR
107 | TOTAL | ALL DIVISIONS | 2519 | 1177 | 343 | 1000 | 177 | 145 | 883 | 216 | 116 | 76 | 150 | 421 | 46.65% | YES | 27 | 84.75% | 38.07% | 46.65%
|  | PATONS represent | 100% | of the total PATONs in D1NR |  | BRIDGES represent | 100% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 46.72% | 2017 Verified, Checked and Added Aid % |  |  | 46.65%
| LIST THREE | SUMMARY BY CG SECTOR |  | VER: COMPLETED TO DATE | COMPARISON TO PLAN
RUNS | PATROL RUNS FOR SECTOR | AUXILIARY DIVISIONS | TOTAL PATONs | VERIFY PATONS | CHECK PATONS | NEED PHOTO | BRDGE PLAN | UNAUT AIDS | VER | CHK | PHO | UNA | BDG | TO GO | % COMP | Made Goal | TO GO | % COMP
26 | SNNE | DIVISION 1 and 2 | 464 | 177 | 69 | 188 | 52 | 78 | 140 | 36 | 24 | 45 | 31 | 70 | 47.63% | YES | 21 | 59.62% | 39.87% | 47.63%
|  | PATONS represent | 18.42% | of the total PATONs in D1NR |  | BRIDGES represent | 29.38% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 38.15% | 2017 Verified, Checked and Added Aids % |  |  | 47.63%
|  | PATONS represent | 18.42% | ONE: of D1NR; FOUR: Bridges represent; THREE: 29.38%; FIVE: of D1NR
32 | SBOS | DIVISIONS 3, 4, 5, 9 AND 12 | 508 | 307 | 95 | 190 | 88 | 35 | 192 | 84 | 15 | 19 | 83 | 126 | 58.07% | YES | 5 | 94.32% | 41.54% | 58.07%
|  | PATONS represent | 20.17% | of the total PATONs in D1NR |  | BRIDGES represent | 49.72% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 60.43% | 2017 Verified, Checked and Added Aids % |  |  | 58.07%
|  | PATONS represent | 20.17% | ONE: of the total PATONs in D1NR; FOUR: Bridges represent; THREE: 49.72%; FIVE: of the total Bridges in D1NR
49 | SSENE | DIVISIONS 6, 7 AND 11 | 1547 | 693 | 179 | 622 | 37 | 32 | 551 | 96 | 77 | 12 | 36 | 225 | 42.6% | YES | 1 | 97.3% | 36.39% | 42.6%
|  | PATONS represent | 61.41% | of the total PATONs in D1NR |  | BRIDGES represent | 20.9% | of the total Bridges in D1NR | Planned Triennial Verification % |  | 44.8% | 2017 Verified, Checked and Added Aids % |  |  | 42.6%
|  | PATONS represent | 61.41% | ONE: of the total PATONs in D1NR; FOUR: Bridges represent; THREE: 20.9%; FIVE: of D1NR
107 | TOTAL | ALL DIVISIONS | 2519 | 1177 | 343 | 1000 | 177 | 145 | 883 | 216 | 116 | 76 | 150 | 421 | 46.65% | YES | 27 | 84.75% | 38.07% | 46.65%
|  | PATONS represent | 100% | of the total PATONs in D1NR |  | BRIDGES represent | 100% | of the total Bridges in D1NR | Planned Triennial Aids Verified % |  | 35.05% | 2017 Verified, Checked and Added Aids % |  |  | 46.65%
Planning and tracking provided by the DSO-NS - Frank Larkin.
Field work performed by the current and qualified Aid Verifiers in First Northern.
Planned Triennial Aids Verified represent the percentage verified versus the planned one-third.
2017 verified, rechecked and submitted for permit represents the percentage completed versus the planned one-third annual verification plan.
In 2017, 46.6% of the total Private Aids were either verified, rechecked or submitted to the PATON System as a new application for a permit in First Northern.

## 2017 SUMMARY NS STATUS (hidden)
2017-09-03
2017 NAVIGATION SYSTEMS STATUS BY AUX DIVISION AS OF 9/2/2017
PATROL RUNS BY DIVISION | Total PATONs | VERIFY PLAN | UNAUTH AIDS | CHECK PLAN | TOTAL PATONS | PHOTOS NEEDED | BRIDGE PLAN
PRIORITY |  | ONE | THREE | TWO |  | THREE | FOUR | COMMENTS FOR MAY, 2017
Div 1 | 215 | 49 | 75 | 24 |  | 88 | 8 | 2017 ACTIVITY - Counting the aids that have been verified, rechecked and the new PATON Application completed for "Unauthorized" PATONs, 37.8% have already been submitted which meets their annual 33.3% objective for 2017. One major final patrol is scheduled for mid September to clean up the rest of the aids and photos on the schedule. |  | 66 | 63 | 8
ANT SWH | Completed | 32 | 45 | 8 | 85 | 18 | 8
SNENE | Qty to go | 17 |  | 16 |  | 70 | 0
33.3% OBJECTIVE |  |  |  | Verified, Rechecked and Unauth Corr'd | 39.53%
Div 2 | 249 | 128 | 3 | 45 |  | 100 | 44 | 2017 ACTIVITY- Counting the aids that have been verified and rechecked, 38.6% have been submitted which meets the Division 2 annual objective for 2017. There are still 103 photos scheduled and 27 bridges to survey in the plan for September. Thanks to all the great NS Staff and AVs in Division 2. |  | 75 | 137 | 44
ANT S PORT | Completed | 108 | 0 | 28 | 136 | 6 | 23 |  |  |  | 1
SNENE | Qty to go | 20 | 3 | 17 |  | 94 | 21
33.3% OBJECTIVE |  | Verified and Unauth Corr'd | 43.37% | Verified, Rechecked and Unauth Corr'd | 54.62% | [5 empty] | 0.7299%
Div 3 | 139 | 107 | 18 | 12 |  | 99 | 13 | SEPTEMBER ACTIVITY - There has be no response from Division 3 to date. Thom Simmons has offered to survey the Division 3 bridges in September. |  | 82 | 87 | 12
ANT BOS | Completed | 49 | 10 | 2 | 61 | 0 | 13
SBOS | Qty to go | 58 | 8 | 10 |  | 99 | 0
33.3% OBJECTIVE |  | Verified and Unauth Corr'd | 42.45% | Verified, Rechecked and Unauth Corr'd | 43.88%
Div 4 | 91 | 70 | 5 | 1 |  | 44 | 9 | SEPTEMBER ACTIVITY - There has be no response from Division 4 to date. The Div 5 NS Team is scheduled to assist in this area during September, weather and crew permitting. Thanks go out to Tony Silvestri, SO-NS Division 5. Thom Simmons from Lake Champlain has offered to do the Division 4 bridges in September. |  | 8 | 41 | 9
ANT BOS | Completed | 13 | 0 | 0 | 13 | 0 | 0
SBOS | Qty to go | 57 | 5 | 1 |  | 44 | 9
33.3% OBJECTIVE |  | Verify and Unauth Corr. | 14.29% | Verified, Rechecked and Unauth Corr'd | 14.29%
Div 5 | 110 | 66 | 3 | 42 |  | 3 | 46 | AUGUST ACTIVITY - Division 5 has completed their PATON and Bridge schedules for the year. All that is left is 3 photos and 2 unauthorized aids. Congratulations to all the great AVs in Division 5 for their support of their PATON and Bridge programs. . . .And, the assistance they have provided to Divisions 4 and 12. |  | 170 | 112 | 15
ANT BOS | Completed | 66 | #REF! | 42 | #REF! | 0 | 46
SBOS | Qty to go | 0 | #REF! | 0 |  | 3 | 0
33.3% OBJECTIVE |  | Verified and Unauth Corr'd | #REF! | Verified, Rechecked and Unauth Corr'd | #REF!
Div 6 | 245 | 132 | 4 | 41 |  | 99 | 6 | AUGUST ACTIVITY - Frank MacKinnon's NS Team deserves a lot of credit for handling the whole of Division 6 and the Westport River AOR in Division 7. It shows what one skilled NS Team can do for the Coast Guard. With all of the members and available facilities in Division 6, it is too bad there is not more support for their PATON and Bridge programs. |  | 64 | 65 | 6
ANT WH | Completed | 109 | 0 | 22 | 131 | 50 | 6
SSENE | Qty to go | 23 | 0 | 19 |  | 49 | 0
33.3% OBJECTIVE |  | Verified and Unauth Corr'd | 44.49% | Verified, Rechecked and Unauth Corr'd | 53.47%
Div 7 | 386 | 154 | 20 | 50 |  | 102 | 15 | AUGUST ACTIVITY - As always, the NS Teams in Narragansett Bay rise to the occasion and complete their annual commitment to the Coast Guard. They have another team assigned to taking the remaining photos. They are also working on cleaning up the open unauthorized aids in the Division . The final numbers for this Division are still coming in. It is a real pleasure working with the Division 7 AVs and NS Staff. |  | 170 | 112 | 15
ANT BRIS | Completed | 147 | 6 | 28 | 181 | 15 | 15
SSENE | Qty to go | 7 | 14 | 22 |  | 87 | 0
33.3% OBJECTIVE |  | Verified and Unauth Corr'd | 39.64% | Verified, Rechecked and Unauth Corr'd | 46.89%
Div 9 | 0 | 0 | 0 | 0 |  | 0 | 14 | AUGUST ACTIVITY - AV Thomas Simmons, who now resides in Vermont, has completed the Conn River bridges in August. which completes this Division's 2017 program. Division 9 has no PATONs on the Connecticut River. They were converted to Mass State Aids in 2016. |  | 54 | 61 | 14
ANT BOS | Completed | 0 | 0 | 0 | 0 | 0 | 11
SBOS | Qty to go | 0 | 0 | 0 |  | 0 | 3
33.3% OBJECTIVE |  | Verified and Unauth Corr'd | N/A | Verified, Rechecked and Unauth Corr'd | N/A
Div 11 | 916 | 407 | 8 | 88 |  | 421 | 16 | AUGUST ACTIVITY - Division 11 completed 36.7 % of their PATON Schedule to date. Reports are still coming in. There is still plenty of work to do with the 403 pending photos and the 15 bridges that are still open. There were some areas that we were not able to reach due to lack of facilities. Overall, it is a great response from Division 11 in 2017. |  | 433 | 490 | 0
ANT WH | Completed | 295 | 6 | 46 | 347 | 12 | 15
SSENE | Qty to go | 112 | 2 | 42 |  | 409 | 1 |  | -
33.3% OBJECTIVE |  | Verify and Unauth Corr. | 32.86% | Verified, Rechecked and Unauth Corr'd | 37.88%
Div 12 | 168 | 64 | 9 | 40 |  | 44 | 7 | AUGUST ACTIVITY - The Division 5 NS Team completed the Quincy, Braintree, Hingham and Weymouth aids and bridges AND the three rivers in Marshfield and Scituate. We are still waiting for the reports from Duxbury, Plymouth and Kingston from Rick Hoadley and Pete Somers. It appears that Division 12 will meet their commitment to the Coast Guard in 2017. |  | 55 | 52 | 7
ANT BOS | Completed | 64 | 6 | 40 | 110 | 15 | 6
SBOS | Qty to go | 0 | 3 | 0 |  | 29 | 1
33.3% OBJECTIVE |  | Verify and Unauth Corr. | 41.67% | Verified, Rechecked and Unauth Corr'd | 65.48%
TOTAL | 2519 | 1177 | 145 | 343 |  | 1000 | 177 | AUGUST SUMMARY - Divisions 3 and 4 in Sector Boston pose completion issues for the 2017 program. However, the numbers reported as verified, rechecked and identified in Harbormaster is currently at 39.1% percent level which exceeds the 33.3% objective for 2018. |  | 1026 | 1109 | 138
Completed to Date |  | 883 | 76 | 216 | 1175 | 116 | 150
Quantity to Go |  | 294 | 69 | 127 |  | 884 | 27
33.3% OBJECTIVE |  | Verify and Unauth Corr'd. | 38.07% | Verified, Rechecked and Unauth Corr'd | 46.65%
There is still time to clean up the unresolved issues and for submission of the reports for the aids that have already been verified or rechecked. The run sheets show the remaining rechecks and photos. There are still many bridges in your area that need to be surveyed. Updated Run Sheets are available from the DSO-NS.
Don't forget to submit your AUXDATA Reports for your 2017 PATON and Bridge activity.
Respectfully submitted,
Frank Larkin, DSO-Navigation Systems
2017-09-01

## Not Used
Annual PLAN Assignments